## Sheet1
Task ID | Title | Assignee | Status | Created At | Completed At | Project | Priority | Comments
TSK001 | Fix login bug | Alice Johnson | Completed | 2025-10-25 10:15:00 | 2025-10-27 14:40:00 | Mobile App | High | Fixed login session issue successfully.
TSK002 | Add search feature | Bob Smith | In Progress | 2025-10-26 09:20:00 |  | Web Platform | Medium | Working on API integration.
TSK003 | Update API docs | Grace Chen | Open | 2025-10-28 13:45:00 |  | API Services | Low | Documentation pending review.
TSK004 | Implement caching | David Lee | Completed | 2025-10-22 11:30:00 | 2025-10-25 15:00:00 | API Services | High | Redis cache implemented for faster response.
TSK005 | Fix payment gateway bug | Emma Wilson | Blocked | 2025-10-29 10:50:00 |  | Web Platform | High | Awaiting API key from vendor.
TSK006 | Create analytics dashboard | Henry Taylor | In Progress | 2025-10-30 08:15:00 |  | Mobile App | High | Building chart components using Chart.js.
TSK007 | Refactor CSS layout | Carol Davis | Completed | 2025-10-25 09:10:00 | 2025-10-26 16:00:00 | Web Platform | Medium | Improved responsiveness on mobile.
TSK008 | Test new release | Iris Anderson | Completed | 2025-10-24 14:00:00 | 2025-10-25 18:30:00 | API Services | Medium | All test cases passed.
TSK009 | Deploy to staging | Frank Martinez | Open | 2025-10-31 12:40:00 |  | Web Platform | Low | Pending code review.
TSK010 | Fix broken links | Shane Williams | Completed | 2025-10-26 10:00:00 | 2025-10-27 19:00:00 | Mobile App | Low | Fixed broken footer links.
TSK011 | Enhance security | Emma Wilson | In Progress | 2025-10-27 16:49:00 | 2025-11-01 16:49:00 | Analytics System | Medium | Code pushed to repo.
TSK012 | Design layout | Iris Anderson | Blocked | 2025-10-29 17:06:00 | 2025-10-30 17:06:00 | API Services | Low | Blocked by dependency.
TSK013 | Deploy version update | Frank Martinez | Completed | 2025-10-28 13:47:00 | 2025-10-31 13:47:00 | Admin Dashboard | High | Blocked by dependency.
TSK014 | Design layout | David Lee | Blocked | 2025-10-24 09:03:00 | 2025-10-26 09:03:00 | API Services | Low | Code pushed to repo.
TSK015 | Create report | Bob Smith | Completed | 2025-10-20 15:36:00 | 2025-10-21 15:36:00 | Admin Dashboard | Medium | Completed successfully.
TSK016 | Fix bug | Henry Taylor | Blocked | 2025-10-26 12:08:00 | 2025-10-30 12:08:00 | Admin Dashboard | Low | Work in progress.
TSK017 | Improve performance | Henry Taylor | Blocked | 2025-10-30 17:28:00 | 2025-11-01 17:28:00 | Web Platform | High | Work in progress.
TSK018 | Create report | Henry Taylor | Open | 2025-10-21 16:52:00 | 2025-10-26 16:52:00 | Web Platform | Low | Pending approval.
TSK019 | Fix bug | Henry Taylor | In Progress | 2025-10-31 18:50:00 |  | API Services | Medium | Waiting for review.
TSK020 | Test new module | Grace Chen | Blocked | 2025-10-26 14:56:00 | 2025-10-31 14:56:00 | Analytics System | High | Completed successfully.
TSK021 | Test new module | Carol Davis | In Progress | 2025-10-22 10:48:00 |  | Admin Dashboard | High | Work in progress.
TSK022 | Add new feature | Carol Davis | Blocked | 2025-10-25 09:51:00 |  | Mobile App | Low | Pending approval.
TSK023 | Fix UI issue | Grace Chen | Open | 2025-10-22 08:21:00 |  | API Services | Medium | Review scheduled.
TSK024 | Enhance security | Henry Taylor | Blocked | 2025-10-31 13:02:00 |  | Mobile App | Low | Need clarification from client.
TSK025 | Design layout | Grace Chen | Open | 2025-10-21 08:10:00 |  | API Services | Medium | Blocked by dependency.
TSK026 | Improve performance | Frank Martinez | On Hold | 2025-10-29 08:40:00 | 2025-11-01 08:40:00 | Analytics System | Medium | Review scheduled.
TSK027 | Enhance security | Henry Taylor | In Progress | 2025-10-21 11:42:00 | 2025-10-25 11:42:00 | API Services | Low | Completed successfully.
TSK028 | Design layout | Bob Smith | Open | 2025-10-30 14:27:00 | 2025-11-01 14:27:00 | Admin Dashboard | High | Code pushed to repo.
TSK029 | Update API | Henry Taylor | Completed | 2025-10-25 11:25:00 |  | Web Platform | Low | Pending approval.
TSK030 | Fix bug | Alice Johnson | In Progress | 2025-10-23 14:34:00 | 2025-10-28 14:34:00 | API Services | High | Under testing.
TSK031 | Deploy version update | Alice Johnson | Completed | 2025-10-25 16:43:00 | 2025-10-28 16:43:00 | Web Platform | High | Code pushed to repo.
TSK032 | Improve performance | Frank Martinez | Open | 2025-10-26 10:57:00 | 2025-10-28 10:57:00 | Mobile App | High | Blocked by dependency.
TSK033 | Add new feature | Carol Davis | Completed | 2025-10-31 14:17:00 |  | Mobile App | High | Waiting for review.
TSK034 | Design layout | Iris Anderson | Completed | 2025-10-25 17:17:00 | 2025-10-27 17:17:00 | Web Platform | Medium | Code pushed to repo.
TSK035 | Design layout | Shane Williams | In Progress | 2025-10-28 10:11:00 | 2025-11-01 10:11:00 | Web Platform | Medium | Blocked by dependency.
TSK036 | Improve performance | Frank Martinez | Blocked | 2025-10-31 09:48:00 |  | Web Platform | Medium | Completed successfully.
TSK037 | Add new feature | Shane Williams | In Progress | 2025-10-26 16:08:00 | 2025-10-29 16:08:00 | Mobile App | High | Under testing.
TSK038 | Create report | Henry Taylor | Blocked | 2025-10-29 12:57:00 | 2025-11-03 12:57:00 | Analytics System | High | Blocked by dependency.
TSK039 | Design layout | Henry Taylor | In Progress | 2025-10-29 09:22:00 | 2025-11-03 09:22:00 | Admin Dashboard | Low | Need clarification from client.
TSK040 | Design layout | Alice Johnson | On Hold | 2025-10-22 18:50:00 |  | Analytics System | High | Need clarification from client.
TSK041 | Test new module | Iris Anderson | Blocked | 2025-10-28 09:53:00 |  | Mobile App | Medium | Code pushed to repo.
TSK042 | Create report | Emma Wilson | On Hold | 2025-10-31 12:53:00 |  | Web Platform | Low | Work in progress.
TSK043 | Create report | Shane Williams | Completed | 2025-10-28 13:15:00 |  | Mobile App | Low | Need clarification from client.
TSK044 | Design layout | Carol Davis | Completed | 2025-10-26 11:03:00 | 2025-10-29 11:03:00 | Admin Dashboard | High | Under testing.
TSK045 | Enhance security | Bob Smith | On Hold | 2025-10-26 09:09:00 | 2025-10-30 09:09:00 | API Services | Low | Waiting for review.
TSK046 | Design layout | Carol Davis | Completed | 2025-10-21 08:49:00 | 2025-10-24 08:49:00 | Analytics System | Low | Under testing.
TSK047 | Improve performance | Alice Johnson | On Hold | 2025-10-31 16:14:00 |  | Mobile App | Low | Blocked by dependency.
TSK048 | Enhance security | Shane Williams | Completed | 2025-10-26 15:36:00 |  | Analytics System | Medium | Blocked by dependency.
TSK049 | Update API | Iris Anderson | In Progress | 2025-10-24 12:00:00 | 2025-10-25 12:00:00 | Mobile App | High | Waiting for review.
TSK050 | Design layout | Grace Chen | Open | 2025-10-24 13:27:00 | 2025-10-28 13:27:00 | Mobile App | Low | Blocked by dependency.
TSK051 | Add new feature | Shane Williams | Completed | 2025-10-28 17:37:00 |  | Web Platform | Medium | Ready for deployment.
TSK052 | Deploy version update | Shane Williams | In Progress | 2025-10-29 16:40:00 |  | Admin Dashboard | High | Blocked by dependency.
TSK053 | Design layout | Carol Davis | On Hold | 2025-10-25 12:39:00 |  | Web Platform | Low | Work in progress.
TSK054 | Enhance security | Henry Taylor | In Progress | 2025-10-23 15:30:00 |  | Mobile App | Low | Code pushed to repo.
TSK055 | Update API | Bob Smith | Completed | 2025-10-24 13:16:00 | 2025-10-26 13:16:00 | API Services | High | Pending approval.
TSK056 | Create report | Emma Wilson | Blocked | 2025-10-28 11:50:00 | 2025-10-30 11:50:00 | Analytics System | High | Code pushed to repo.
TSK057 | Improve performance | Shane Williams | Blocked | 2025-10-29 10:04:00 | 2025-11-02 10:04:00 | Web Platform | Medium | Under testing.
TSK058 | Add new feature | Bob Smith | Open | 2025-10-30 13:37:00 | 2025-11-02 13:37:00 | API Services | Medium | Work in progress.
TSK059 | Improve performance | Iris Anderson | In Progress | 2025-10-26 13:49:00 |  | Admin Dashboard | Low | Under testing.
TSK060 | Create report | Shane Williams | Completed | 2025-10-20 09:30:00 | 2025-10-25 09:30:00 | API Services | Low | Code pushed to repo.
TSK061 | Improve performance | Bob Smith | Blocked | 2025-10-20 14:43:00 | 2025-10-22 14:43:00 | Mobile App | Medium | Ready for deployment.
TSK062 | Test new module | Bob Smith | In Progress | 2025-10-29 17:19:00 | 2025-10-30 17:19:00 | API Services | Medium | Work in progress.
TSK063 | Update API | Frank Martinez | Open | 2025-10-30 17:44:00 | 2025-11-03 17:44:00 | Mobile App | Low | Blocked by dependency.
TSK064 | Fix bug | David Lee | Blocked | 2025-10-28 17:18:00 |  | API Services | High | Completed successfully.
TSK065 | Fix bug | Henry Taylor | In Progress | 2025-10-25 14:05:00 |  | API Services | Medium | Work in progress.
TSK066 | Fix UI issue | Emma Wilson | Completed | 2025-10-24 16:46:00 |  | Admin Dashboard | High | Pending approval.
TSK067 | Deploy version update | Frank Martinez | Open | 2025-10-30 12:32:00 |  | Admin Dashboard | Low | Pending approval.
TSK068 | Design layout | Carol Davis | In Progress | 2025-10-31 12:47:00 |  | Web Platform | High | Need clarification from client.
TSK069 | Deploy version update | Henry Taylor | Completed | 2025-10-26 13:19:00 |  | Admin Dashboard | High | Completed successfully.
TSK070 | Fix bug | Alice Johnson | Open | 2025-10-25 10:15:00 |  | Analytics System | Low | Work in progress.
TSK071 | Enhance security | Frank Martinez | Completed | 2025-10-27 17:49:00 | 2025-10-29 17:49:00 | Mobile App | Low | Ready for deployment.
TSK072 | Design layout | Shane Williams | Open | 2025-10-31 11:53:00 |  | Web Platform | High | Code pushed to repo.
TSK073 | Fix bug | Frank Martinez | In Progress | 2025-10-24 08:50:00 |  | API Services | Medium | Review scheduled.
TSK074 | Create report | Emma Wilson | Open | 2025-10-29 09:20:00 | 2025-11-02 09:20:00 | Web Platform | High | Blocked by dependency.
TSK075 | Fix UI issue | Grace Chen | On Hold | 2025-10-25 15:23:00 |  | Web Platform | High | Pending approval.
TSK076 | Design layout | Carol Davis | Open | 2025-10-28 14:36:00 | 2025-11-02 14:36:00 | Mobile App | Medium | Work in progress.
TSK077 | Create report | Iris Anderson | Completed | 2025-10-31 12:01:00 | 2025-11-02 12:01:00 | Web Platform | Low | Code pushed to repo.
TSK078 | Fix UI issue | Frank Martinez | In Progress | 2025-10-26 16:08:00 |  | Web Platform | High | Blocked by dependency.
TSK079 | Enhance security | Emma Wilson | On Hold | 2025-10-22 11:27:00 | 2025-10-24 11:27:00 | Admin Dashboard | Medium | Under testing.
TSK080 | Design layout | Henry Taylor | On Hold | 2025-10-22 14:32:00 |  | Mobile App | High | Ready for deployment.
TSK081 | Fix bug | Alice Johnson | Completed | 2025-10-22 16:48:00 |  | Analytics System | Medium | Work in progress.
TSK082 | Add new feature | Grace Chen | Open | 2025-10-26 10:38:00 | 2025-10-27 10:38:00 | Admin Dashboard | Low | Waiting for review.
TSK083 | Add new feature | Henry Taylor | On Hold | 2025-10-21 13:50:00 | 2025-10-24 13:50:00 | Mobile App | Medium | Completed successfully.
TSK084 | Create report | Alice Johnson | On Hold | 2025-10-26 15:16:00 | 2025-10-30 15:16:00 | API Services | High | Under testing.
TSK085 | Test new module | Shane Williams | On Hold | 2025-10-26 15:03:00 | 2025-10-31 15:03:00 | API Services | Medium | Ready for deployment.
TSK086 | Add new feature | Bob Smith | Completed | 2025-10-26 12:10:00 | 2025-10-29 12:10:00 | Mobile App | Low | Pending approval.
TSK087 | Design layout | Frank Martinez | Open | 2025-10-30 10:40:00 |  | Web Platform | Medium | Code pushed to repo.
TSK088 | Add new feature | Bob Smith | Open | 2025-10-26 12:37:00 | 2025-10-29 12:37:00 | Mobile App | High | Review scheduled.
TSK089 | Deploy version update | Iris Anderson | In Progress | 2025-10-22 18:10:00 |  | Analytics System | Low | Blocked by dependency.
TSK090 | Design layout | Henry Taylor | In Progress | 2025-10-29 12:33:00 |  | Mobile App | High | Pending approval.
TSK091 | Add new feature | Frank Martinez | On Hold | 2025-10-30 13:24:00 | 2025-10-31 13:24:00 | API Services | Low | Blocked by dependency.
TSK092 | Update API | Frank Martinez | On Hold | 2025-10-23 14:23:00 | 2025-10-25 14:23:00 | Analytics System | Medium | Ready for deployment.
TSK093 | Fix bug | Carol Davis | Completed | 2025-10-26 17:18:00 |  | Analytics System | High | Code pushed to repo.
TSK094 | Create report | Grace Chen | Open | 2025-10-28 16:38:00 |  | Mobile App | High | Ready for deployment.
TSK095 | Design layout | Bob Smith | Completed | 2025-10-29 11:36:00 | 2025-11-01 11:36:00 | Admin Dashboard | Medium | Ready for deployment.
TSK096 | Design layout | Bob Smith | On Hold | 2025-10-24 11:59:00 |  | API Services | Low | Under testing.
TSK097 | Fix bug | Henry Taylor | Completed | 2025-10-27 17:33:00 | 2025-11-01 17:33:00 | API Services | High | Need clarification from client.
TSK098 | Fix bug | Emma Wilson | On Hold | 2025-10-23 13:14:00 | 2025-10-28 13:14:00 | Mobile App | Low | Work in progress.
TSK099 | Design layout | Alice Johnson | Blocked | 2025-10-21 18:12:00 | 2025-10-23 18:12:00 | Admin Dashboard | Medium | Review scheduled.
TSK100 | Deploy version update | Frank Martinez | Blocked | 2025-10-29 18:32:00 | 2025-10-30 18:32:00 | Analytics System | High | Ready for deployment.