## Tasks
Task ID | Title | Component | Subcomponent | Component Owner | Assignee | Status | Progress % | Estimated Hours | Estimated Cost (USD) | Dependencies | Priority | Project | Created At | Completed At | Comments | Tags
BIG0001 | UI: Landing - Test | UI | Landing | James Scott | James Scott | In Progress | 69 | 40 | 1800 | BIG0012 | Low | Core Platform | 2025-09-18 10:43:00 |  | Owner to update status. | performance,security,research
BIG0002 | Security: Encryption - Implement | Security | Encryption | Noah Davis | Noah Davis | Blocked | 43 | 16 | 560 |  | Low | Analytics Suite | 2025-09-01 11:44:00 |  | QA passed. | bug,critical
BIG0003 | Search: Filters - Improve | Search | Filters | Noah Davis | Noah Davis | Blocked | 80 | 12 | 300 | BIG0080 | Medium | API Services | 2025-10-19 10:35:00 |  | Blocked by API team. | design
BIG0004 | Database: Schema - Refactor | Database | Schema | Mia Lewis | James Scott | In Progress | 26 | 12 | 420 | BIG0086 | High | API Services | 2025-10-17 11:23:00 |  | Blocked by API team. | research,enhancement,refactor
BIG0005 | Payments: Refunds - Test | Payments | Refunds | Priya Singh | Priya Singh | In Progress | 40 | 4 | 100 | BIG0052 | Low | Admin Dashboard | 2025-10-12 09:14:00 |  | QA passed. | minor,refactor
BIG0006 | Payments: Gateway Integration - Implement | Payments | Gateway Integration | Priya Singh | Priya Singh | Blocked | 51 | 24 | 600 |  | Critical | Mobile App | 2025-11-14 15:57:00 |  | Merge conflict to resolve. | bug
BIG0007 | API: API Docs - Design | API | API Docs | Liam Brown | Mason Hall | In Progress | 70 | 12 | 420 |  | Medium | Admin Dashboard | 2025-11-16 16:33:00 |  | Docs required. | design
BIG0008 | API: API Docs - Improve | API | API Docs | Rohan Iyer | James Scott | Review | 80 | 4 | 140 |  | Low | Analytics Suite | 2025-09-23 17:58:00 |  | Needs performance tests. | ux
BIG0009 | DevOps: CI/CD - Improve | DevOps | CI/CD | Sophia Clark | Sophia Clark | Completed | 100 | 4 | 140 | BIG0094 | High | Analytics Suite | 2025-10-10 12:03:00 | 2025-10-14 13:03:00 | Needs performance tests. | security,enhancement
BIG0010 | Security: AuthZ - Refactor | Security | AuthZ | Elijah Green | Elijah Green | Review | 51 | 12 | 420 | BIG0086 | Medium | Admin Dashboard | 2025-11-28 12:45:00 |  | Merge conflict to resolve. | bug
BIG0011 | Auth: OAuth - Design | Auth | OAuth | Amelia Baker | Amelia Baker | Open | 4 | 4 | 180 |  | Medium | Web Portal | 2025-11-30 09:14:00 |  | Merge conflict to resolve. | ux
BIG0012 | DevOps: CI/CD - Refactor | DevOps | CI/CD | Olivia Miller | Olivia Miller | Open | 52 | 16 | 400 |  | Medium | API Services | 2025-09-13 15:22:00 |  | Blocked by API team. | critical,bug,research
BIG0013 | Database: Backups - Implement | Database | Backups | Amelia Baker | Olivia Miller | Open | 56 | 4 | 140 |  | Low | Admin Dashboard | 2025-10-30 12:55:00 |  | Requires design sign-off. | minor
BIG0014 | DevOps: CI/CD - Refactor | DevOps | CI/CD | Arjun Kumar | Liam Roberts | Open | 36 | 16 | 400 | BIG0055 | Low | Web Portal | 2025-09-01 15:16:00 |  | Owner to update status. | security,performance,critical
BIG0015 | Auth: Password Reset - Design | Auth | Password Reset | Rohan Iyer | Rohan Iyer | Open | 8 | 8 | 280 |  | Medium | Mobile App | 2025-11-05 10:54:00 |  | Pending security review. | research,performance,bug
BIG0016 | Search: Ranking - Design | Search | Ranking | Liam Brown | Liam Brown | Review | 50 | 12 | 540 | BIG0017 | Medium | Analytics Suite | 2025-09-27 14:15:00 |  | Blocked by API team. | ux,bug,security
BIG0017 | Database: Indexes - Implement | Database | Indexes | Priya Singh | Sophia Clark | Completed | 100 | 24 | 840 | BIG0091 | Medium | Analytics Suite | 2025-10-02 14:18:00 | 2025-10-05 21:18:00 | Requires design sign-off. | bug,enhancement
BIG0018 | UI: Landing - Test | UI | Landing | Priya Singh | Priya Singh | Open | 26 | 12 | 300 | BIG0088 | Medium | Web Portal | 2025-10-07 12:45:00 |  | Requires design sign-off. | design,performance
BIG0019 | Notifications: Push - Test | Notifications | Push | Sophia Clark | James Scott | Open | 71 | 16 | 400 |  | Low | API Services | 2025-10-27 17:45:00 |  | Needs performance tests. | security,enhancement,minor
BIG0020 | Auth: Session - Fix | Auth | Session | Mia Lewis | Liam Roberts | Completed | 100 | 24 | 1080 |  | High | Mobile App | 2025-09-27 12:42:00 | 2025-09-29 17:42:00 | Needs performance tests. | performance,enhancement
BIG0021 | Notifications: Email - Test | Notifications | Email | Amelia Baker | Amelia Baker | In Progress | 60 | 4 | 100 |  | High | Billing System | 2025-11-29 10:24:00 |  | QA passed. | research
BIG0022 | Database: Backups - Fix | Database | Backups | James Scott | James Scott | Completed | 100 | 40 | 1800 | BIG0069 | High | Core Platform | 2025-10-06 14:41:00 | 2025-10-15 20:41:00 | Docs required. | performance,bug
BIG0023 | Analytics: Dashboards - Test | Analytics | Dashboards | Liam Brown | Liam Brown | In Progress | 24 | 24 | 1080 |  | High | Core Platform | 2025-11-05 10:24:00 |  | Owner to update status. | critical
BIG0024 | Notifications: SMS - Improve | Notifications | SMS | Mia Lewis | Harper Adams | Blocked | 89 | 16 | 720 |  | Low | API Services | 2025-11-25 15:20:00 |  | Pending security review. | ux,design,minor
BIG0025 | Auth: Session - Fix | Auth | Session | Harper Adams | Elijah Green | In Progress | 56 | 16 | 400 |  | Medium | Analytics Suite | 2025-11-14 14:29:00 |  | Needs performance tests. | ux,critical,bug
BIG0026 | Payments: Gateway Integration - Implement | Payments | Gateway Integration | Lucas Young | Lucas Young | Open | 58 | 4 | 100 |  | High | Billing System | 2025-10-02 16:39:00 |  | Merge conflict to resolve. | performance
BIG0027 | Analytics: Events - Implement | Analytics | Events | Noah Davis | Rohan Iyer | In Progress | 58 | 4 | 100 | BIG0018 | Medium | Admin Dashboard | 2025-11-11 12:58:00 |  | QA passed. | security,minor,refactor
BIG0028 | DevOps: Infrastructure - Fix | DevOps | Infrastructure | Mason Hall | Amelia Baker | Completed | 100 | 16 | 400 | BIG0010 | Low | Web Portal | 2025-10-06 17:31:00 | 2025-10-10 21:31:00 | QA passed. | enhancement
BIG0029 | Analytics: ETL - Implement | Analytics | ETL | Arjun Kumar | Elijah Green | Open | 53 | 16 | 560 |  | High | Billing System | 2025-10-23 14:34:00 |  | Requires design sign-off. | refactor,performance
BIG0030 | Payments: Billing - Refactor | Payments | Billing | Noah Davis | Priya Singh | Completed | 100 | 16 | 720 |  | Medium | API Services | 2025-11-09 12:31:00 | 2025-11-13 16:31:00 | Pending security review. | ux
BIG0031 | Auth: Password Reset - Design | Auth | Password Reset | Arjun Kumar | Arjun Kumar | Completed | 100 | 4 | 140 | BIG0034 | Medium | Billing System | 2025-09-11 15:08:00 | 2025-09-19 17:08:00 | QA passed. | design,minor
BIG0032 | UI: Components - Improve | UI | Components | Amelia Baker | Priya Singh | Open | 83 | 4 | 180 |  | High | Mobile App | 2025-10-15 12:41:00 |  | Requires design sign-off. | refactor
BIG0033 | UI: Dashboard - Refactor | UI | Dashboard | James Scott | James Scott | Completed | 100 | 4 | 100 |  | High | Admin Dashboard | 2025-09-22 10:49:00 | 2025-09-25 14:49:00 | Pending security review. | research,bug,ux
BIG0034 | Payments: Refunds - Design | Payments | Refunds | Zara Patel | Ella Johnson | Completed | 100 | 40 | 1400 |  | Medium | Web Portal | 2025-11-12 09:22:00 | 2025-11-21 15:22:00 | Requires design sign-off. | minor
BIG0035 | DevOps: Monitoring - Implement | DevOps | Monitoring | Olivia Miller | Olivia Miller | Open | 61 | 24 | 840 | BIG0060 | High | Admin Dashboard | 2025-11-06 13:39:00 |  | Docs required. | bug
BIG0036 | DevOps: CI/CD - Refactor | DevOps | CI/CD | Arjun Kumar | Arjun Kumar | Completed | 100 | 8 | 360 |  | Medium | Web Portal | 2025-10-19 14:01:00 | 2025-10-27 19:01:00 | QA passed. | design,security,performance
BIG0037 | Database: Schema - Implement | Database | Schema | Harper Adams | Olivia Miller | In Progress | 62 | 40 | 1800 |  | Low | Mobile App | 2025-10-01 16:41:00 |  | Pending security review. | ux,critical,refactor
BIG0038 | Security: Encryption - Refactor | Security | Encryption | Mia Lewis | Priya Singh | In Progress | 32 | 12 | 540 |  | High | Web Portal | 2025-11-29 16:17:00 |  | Blocked by API team. | research
BIG0039 | DevOps: Infrastructure - Test | DevOps | Infrastructure | Arjun Kumar | Arjun Kumar | Review | 37 | 8 | 280 | BIG0030 | Low | Core Platform | 2025-11-07 13:06:00 |  | Needs performance tests. | security
BIG0040 | API: API Docs - Improve | API | API Docs | Ethan Walker | Ava Thompson | Blocked | 23 | 12 | 300 | BIG0007 | High | Billing System | 2025-10-31 16:28:00 |  | Blocked by API team. | bug,performance
BIG0041 | API: Rate Limiting - Improve | API | Rate Limiting | Amelia Baker | Amelia Baker | Open | 48 | 24 | 1080 | BIG0058 | Low | Admin Dashboard | 2025-10-24 12:49:00 |  | Pending security review. | performance,bug,research
BIG0042 | Database: Indexes - Test | Database | Indexes | Mason Hall | Mason Hall | Open | 0 | 8 | 200 | BIG0053 | Medium | Billing System | 2025-09-23 17:04:00 |  | Docs required. | design,refactor
BIG0043 | Database: Indexes - Test | Database | Indexes | Arjun Kumar | Arjun Kumar | Completed | 100 | 40 | 1400 | BIG0020 | High | Core Platform | 2025-09-26 15:07:00 | 2025-10-05 18:07:00 | Requires design sign-off. | ux,design
BIG0044 | UI: Components - Test | UI | Components | Ava Thompson | Harper Adams | Completed | 100 | 4 | 180 |  | High | API Services | 2025-10-05 17:34:00 | 2025-10-14 00:34:00 | QA passed. | research
BIG0045 | Search: Ranking - Improve | Search | Ranking | Zara Patel | James Scott | Blocked | 56 | 40 | 1400 |  | Critical | Billing System | 2025-09-23 16:33:00 |  | Merge conflict to resolve. | minor,critical
BIG0046 | UI: Dashboard - Fix | UI | Dashboard | Ava Thompson | Olivia Miller | Completed | 100 | 16 | 400 | BIG0012 | Low | Core Platform | 2025-10-07 15:52:00 | 2025-10-16 15:52:00 | Pending security review. | security,refactor,minor
BIG0047 | Database: Indexes - Design | Database | Indexes | Harper Adams | Zara Patel | Completed | 100 | 12 | 300 | BIG0057 | Low | API Services | 2025-09-07 12:17:00 | 2025-09-16 14:17:00 | Owner to update status. | performance,security,minor
BIG0048 | Database: Schema - Refactor | Database | Schema | Lucas Young | Ella Johnson | Completed | 100 | 40 | 1800 | BIG0035 | High | Billing System | 2025-09-20 16:59:00 | 2025-09-26 00:59:00 | Owner to update status. | research,security
BIG0049 | API: REST Endpoints - Fix | API | REST Endpoints | Noah Davis | Olivia Miller | In Progress | 36 | 4 | 180 | BIG0093 | High | Admin Dashboard | 2025-11-04 13:52:00 |  | Merge conflict to resolve. | refactor,critical,security
BIG0050 | Security: Encryption - Refactor | Security | Encryption | Liam Brown | Liam Brown | Completed | 100 | 16 | 400 | BIG0006 | High | API Services | 2025-11-29 12:36:00 | 2025-12-06 15:36:00 | Pending security review. | enhancement,refactor,performance
BIG0051 | Security: AuthZ - Fix | Security | AuthZ | James Scott | Ella Johnson | Completed | 100 | 40 | 1800 | BIG0019 | High | Mobile App | 2025-10-27 10:33:00 | 2025-11-04 10:33:00 | Blocked by API team. | ux,minor
BIG0052 | UI: Forms - Test | UI | Forms | Mason Hall | Priya Singh | In Progress | 4 | 24 | 840 |  | Low | API Services | 2025-10-11 16:55:00 |  | Docs required. | bug,ux
BIG0053 | API: Rate Limiting - Improve | API | Rate Limiting | Liam Roberts | Liam Roberts | In Progress | 55 | 12 | 420 |  | Medium | Admin Dashboard | 2025-09-08 13:22:00 |  | Needs performance tests. | ux
BIG0054 | Search: Ranking - Implement | Search | Ranking | Priya Singh | Zara Patel | Review | 32 | 40 | 1400 | BIG0059 | Medium | Analytics Suite | 2025-09-19 12:29:00 |  | Merge conflict to resolve. | bug
BIG0055 | Notifications: SMS - Fix | Notifications | SMS | Harper Adams | Olivia Miller | Completed | 100 | 4 | 140 | BIG0031 | Medium | Admin Dashboard | 2025-10-29 13:12:00 | 2025-11-05 20:12:00 | Docs required. | minor
BIG0056 | Auth: Login - Design | Auth | Login | Liam Roberts | Zara Patel | Completed | 100 | 40 | 1800 | BIG0025 | Medium | API Services | 2025-10-07 12:38:00 | 2025-10-13 15:38:00 | Needs performance tests. | refactor,performance
BIG0057 | Notifications: SMS - Implement | Notifications | SMS | Mason Hall | Mason Hall | Review | 16 | 8 | 200 | BIG0070 | Medium | Web Portal | 2025-10-12 15:11:00 |  | Needs performance tests. | design,critical
BIG0058 | DevOps: CI/CD - Implement | DevOps | CI/CD | Amelia Baker | Amelia Baker | Completed | 100 | 4 | 100 |  | Low | Core Platform | 2025-11-26 15:54:00 | 2025-12-05 20:54:00 | Merge conflict to resolve. | design,minor,critical
BIG0059 | Database: Backups - Improve | Database | Backups | Sana Roy | Sana Roy | Completed | 100 | 40 | 1400 | BIG0009 | High | Web Portal | 2025-11-11 14:58:00 | 2025-11-21 17:58:00 | Pending security review. | performance
BIG0060 | DevOps: CI/CD - Improve | DevOps | CI/CD | Sana Roy | Amelia Baker | Completed | 100 | 16 | 720 |  | High | API Services | 2025-09-18 15:29:00 | 2025-09-24 23:29:00 | Blocked by API team. | design,performance
BIG0061 | Notifications: Push - Refactor | Notifications | Push | Noah Davis | Noah Davis | Review | 69 | 12 | 540 | BIG0083 | Low | Web Portal | 2025-10-17 10:43:00 |  | Owner to update status. | research
BIG0062 | Search: Indexing - Improve | Search | Indexing | Sana Roy | Liam Brown | In Progress | 26 | 24 | 600 |  | High | Mobile App | 2025-09-17 12:04:00 |  | QA passed. | design
BIG0063 | API: Rate Limiting - Implement | API | Rate Limiting | Rohan Iyer | Ella Johnson | Completed | 100 | 24 | 840 |  | Low | Core Platform | 2025-09-04 11:00:00 | 2025-09-10 14:00:00 | Needs performance tests. | bug
BIG0064 | DevOps: Infrastructure - Design | DevOps | Infrastructure | Ethan Walker | Arjun Kumar | Open | 93 | 4 | 180 | BIG0085 | Medium | Core Platform | 2025-11-04 12:39:00 |  | Requires design sign-off. | bug,refactor
BIG0065 | DevOps: CI/CD - Improve | DevOps | CI/CD | Sana Roy | Liam Brown | Completed | 100 | 40 | 1800 | BIG0042 | Critical | Admin Dashboard | 2025-09-09 11:17:00 | 2025-09-19 19:17:00 | Docs required. | bug,ux
BIG0066 | Security: AuthZ - Implement | Security | AuthZ | Olivia Miller | Olivia Miller | In Progress | 51 | 16 | 400 |  | Medium | Web Portal | 2025-09-30 15:21:00 |  | Docs required. | refactor
BIG0067 | UI: Landing - Improve | UI | Landing | Olivia Miller | Olivia Miller | Open | 75 | 4 | 140 | BIG0072 | Medium | Billing System | 2025-10-18 11:35:00 |  | QA passed. | performance,design,security
BIG0068 | UI: Dashboard - Implement | UI | Dashboard | Sana Roy | Zara Patel | In Progress | 47 | 24 | 600 | BIG0015 | Medium | Analytics Suite | 2025-09-14 14:54:00 |  | Pending security review. | security,performance,design
BIG0069 | API: Rate Limiting - Test | API | Rate Limiting | Harper Adams | Harper Adams | Review | 72 | 8 | 280 | BIG0085 | Low | API Services | 2025-10-15 09:11:00 |  | Requires design sign-off. | research,minor,security
BIG0070 | Notifications: Push - Fix | Notifications | Push | Zara Patel | Harper Adams | Completed | 100 | 8 | 200 |  | Medium | Web Portal | 2025-11-12 10:56:00 | 2025-11-13 12:56:00 | Merge conflict to resolve. | refactor,minor,design
BIG0071 | Security: Vulnerability Fixes - Fix | Security | Vulnerability Fixes | Olivia Miller | Olivia Miller | Open | 39 | 40 | 1400 |  | Medium | Admin Dashboard | 2025-11-26 16:33:00 |  | Requires design sign-off. | research,enhancement
BIG0072 | Payments: Billing - Improve | Payments | Billing | Ava Thompson | Ava Thompson | In Progress | 68 | 16 | 560 |  | Medium | Analytics Suite | 2025-10-26 11:08:00 |  | QA passed. | performance,minor,ux
BIG0073 | UI: Forms - Design | UI | Forms | Sophia Clark | Olivia Miller | Blocked | 51 | 4 | 100 | BIG0003 | Low | Admin Dashboard | 2025-11-30 15:18:00 |  | Merge conflict to resolve. | minor
BIG0074 | Database: Backups - Design | Database | Backups | Elijah Green | Ethan Walker | Blocked | 28 | 12 | 300 |  | Low | API Services | 2025-10-21 13:47:00 |  | Blocked by API team. | critical,enhancement
BIG0075 | UI: Dashboard - Fix | UI | Dashboard | Liam Brown | Elijah Green | Open | 63 | 40 | 1000 | BIG0060 | Medium | Admin Dashboard | 2025-09-20 10:11:00 |  | QA passed. | refactor
BIG0076 | DevOps: Infrastructure - Test | DevOps | Infrastructure | Harper Adams | Harper Adams | Completed | 100 | 12 | 540 | BIG0060 | Low | Web Portal | 2025-11-15 09:22:00 | 2025-11-24 10:22:00 | Docs required. | ux
BIG0077 | Security: Encryption - Refactor | Security | Encryption | Noah Davis | Arjun Kumar | Blocked | 83 | 24 | 1080 | BIG0025 | Medium | Admin Dashboard | 2025-09-06 16:58:00 |  | Needs performance tests. | critical
BIG0078 | UI: Dashboard - Improve | UI | Dashboard | Liam Roberts | Amelia Baker | Completed | 100 | 12 | 300 | BIG0048 | Medium | Analytics Suite | 2025-10-27 17:33:00 | 2025-11-06 19:33:00 | QA passed. | critical,bug,ux
BIG0079 | Security: AuthZ - Refactor | Security | AuthZ | Harper Adams | Harper Adams | In Progress | 74 | 4 | 180 |  | High | Web Portal | 2025-11-24 11:21:00 |  | Pending security review. | bug,design,minor
BIG0080 | Notifications: Push - Test | Notifications | Push | Zara Patel | Rohan Iyer | Open | 2 | 12 | 300 | BIG0047 | Low | Mobile App | 2025-11-25 15:32:00 |  | QA passed. | research
BIG0081 | API: REST Endpoints - Fix | API | REST Endpoints | Ella Johnson | Ella Johnson | Blocked | 43 | 40 | 1000 |  | Medium | Mobile App | 2025-11-09 17:02:00 |  | Needs performance tests. | ux,enhancement,refactor
BIG0082 | Analytics: Dashboards - Test | Analytics | Dashboards | Elijah Green | Amelia Baker | Review | 57 | 40 | 1400 |  | Medium | Analytics Suite | 2025-11-18 13:48:00 |  | Merge conflict to resolve. | ux,refactor
BIG0083 | Payments: Billing - Design | Payments | Billing | Ella Johnson | Rohan Iyer | In Progress | 17 | 24 | 600 |  | Medium | Analytics Suite | 2025-09-21 12:51:00 |  | QA passed. | security,bug,design
BIG0084 | API: Rate Limiting - Refactor | API | Rate Limiting | Rohan Iyer | Rohan Iyer | Open | 57 | 8 | 200 |  | Medium | Billing System | 2025-10-26 10:58:00 |  | QA passed. | critical
BIG0085 | Auth: Session - Improve | Auth | Session | Liam Brown | Liam Brown | Completed | 100 | 40 | 1800 | BIG0061 | Medium | Core Platform | 2025-09-18 09:18:00 | 2025-09-26 11:18:00 | Requires design sign-off. | security
BIG0086 | Search: Ranking - Refactor | Search | Ranking | Ava Thompson | Ella Johnson | Completed | 100 | 16 | 560 | BIG0082 | Low | Analytics Suite | 2025-10-01 13:07:00 | 2025-10-02 16:07:00 | Merge conflict to resolve. | security,research,enhancement
BIG0087 | Analytics: Events - Design | Analytics | Events | Sophia Clark | Sophia Clark | In Progress | 10 | 40 | 1400 | BIG0068 | Low | Admin Dashboard | 2025-10-24 11:42:00 |  | Requires design sign-off. | performance,minor
BIG0088 | Payments: Refunds - Improve | Payments | Refunds | Noah Davis | Sophia Clark | Completed | 100 | 8 | 200 | BIG0006 | Medium | Analytics Suite | 2025-10-15 12:46:00 | 2025-10-17 17:46:00 | Needs performance tests. | refactor,enhancement,security
BIG0089 | DevOps: CI/CD - Fix | DevOps | CI/CD | Elijah Green | Elijah Green | Open | 65 | 12 | 420 | BIG0051 | Low | Analytics Suite | 2025-09-26 09:20:00 |  | Owner to update status. | critical
BIG0090 | UI: Forms - Refactor | UI | Forms | Ethan Walker | Ethan Walker | Completed | 100 | 12 | 420 | BIG0067 | High | API Services | 2025-10-20 14:11:00 | 2025-10-28 21:11:00 | Pending security review. | enhancement,security,design
BIG0091 | UI: Landing - Fix | UI | Landing | Olivia Miller | Harper Adams | In Progress | 56 | 40 | 1800 | BIG0045 | Low | Analytics Suite | 2025-11-17 15:10:00 |  | QA passed. | performance,bug
BIG0092 | Analytics: Dashboards - Design | Analytics | Dashboards | Noah Davis | Mia Lewis | Review | 8 | 8 | 200 | BIG0031 | Medium | Admin Dashboard | 2025-09-19 16:02:00 |  | Requires design sign-off. | critical,refactor
BIG0093 | Search: Indexing - Design | Search | Indexing | Sophia Clark | Sophia Clark | In Progress | 3 | 4 | 180 |  | Medium | Billing System | 2025-11-23 13:15:00 |  | Blocked by API team. | refactor,research
BIG0094 | Payments: Refunds - Refactor | Payments | Refunds | Harper Adams | Elijah Green | Open | 56 | 40 | 1400 | BIG0012 | Medium | API Services | 2025-09-10 16:11:00 |  | Blocked by API team. | enhancement,ux
BIG0095 | Security: Vulnerability Fixes - Improve | Security | Vulnerability Fixes | Mason Hall | Elijah Green | Completed | 100 | 24 | 840 | BIG0048 | High | Admin Dashboard | 2025-10-01 16:01:00 | 2025-10-08 00:01:00 | Needs performance tests. | design
BIG0096 | DevOps: Monitoring - Refactor | DevOps | Monitoring | Lucas Young | Olivia Miller | Completed | 100 | 16 | 400 | BIG0088 | Low | Analytics Suite | 2025-09-10 11:20:00 | 2025-09-12 18:20:00 | Needs performance tests. | security,performance
BIG0097 | Security: Vulnerability Fixes - Fix | Security | Vulnerability Fixes | Mia Lewis | Mia Lewis | Open | 36 | 24 | 600 | BIG0011 | Low | Admin Dashboard | 2025-11-30 12:22:00 |  | Docs required. | ux,security
BIG0098 | Security: AuthZ - Implement | Security | AuthZ | Ava Thompson | Arjun Kumar | Review | 92 | 24 | 1080 | BIG0078 | High | Admin Dashboard | 2025-09-20 11:42:00 |  | Requires design sign-off. | performance
BIG0099 | Search: Filters - Test | Search | Filters | Elijah Green | Elijah Green | Completed | 100 | 40 | 1000 | BIG0039 | Low | Analytics Suite | 2025-10-24 09:31:00 | 2025-11-02 13:31:00 | Pending security review. | performance
BIG0100 | DevOps: Infrastructure - Refactor | DevOps | Infrastructure | Ella Johnson | Noah Davis | In Progress | 40 | 40 | 1000 | BIG0094 | Critical | Mobile App | 2025-11-17 11:20:00 |  | QA passed. | research,refactor

## Component_Summary
Component | Task Count
DevOps | 15
UI | 14
Security | 12
Database | 11
API | 10
Payments | 9
Search | 8
Notifications | 8
Auth | 7
Analytics | 6