## Tasks
Task ID | Title | Component | Subcomponent | Component Owner | Assignee | Status | Progress % | Estimated Hours | Estimated Cost (USD) | Dependencies | Priority | Project | Created At | Completed At | Comments | Tags
BIG1001 | Payments: Billing - Implement | Payments | Billing | Lucas Young | Lucas Young | Open | 53 | 24 | 1080 |  | High | Admin Dashboard | 2025-10-08 15:55:00 |  | QA passed. | refactor
BIG1002 | DevOps: Infrastructure - Fix | DevOps | Infrastructure | Zara Patel | Zara Patel | Open | 27 | 8 | 200 | BIG1075 | Low | Web Portal | 2025-10-21 17:29:00 |  | Merge conflict to resolve. | security,performance
BIG1003 | Analytics: Events - Fix | Analytics | Events | James Scott | Sophia Clark | Completed | 100 | 8 | 200 | BIG1047 | Low | Admin Dashboard | 2025-10-17 09:25:00 | 2025-10-18 17:25:00 | Merge conflict to resolve. | ux,bug,enhancement
BIG1004 | Analytics: Dashboards - Fix | Analytics | Dashboards | Rohan Iyer | Priya Singh | Review | 51 | 24 | 600 |  | Low | Mobile App | 2025-09-19 12:38:00 |  | QA passed. | enhancement,security
BIG1005 | Notifications: SMS - Fix | Notifications | SMS | Sophia Clark | Mia Lewis | In Progress | 64 | 12 | 540 | BIG1066 | High | Web Portal | 2025-11-18 13:37:00 |  | Merge conflict to resolve. | bug,minor
BIG1006 | Payments: Refunds - Test | Payments | Refunds | Ava Thompson | Ava Thompson | Blocked | 74 | 4 | 100 |  | Medium | API Services | 2025-10-04 12:46:00 |  | Pending security review. | research,performance,bug
BIG1007 | Auth: Password Reset - Fix | Auth | Password Reset | Zara Patel | Olivia Miller | Open | 78 | 24 | 840 |  | High | Admin Dashboard | 2025-11-28 12:26:00 |  | Owner to update status. | minor,critical,enhancement
BIG1008 | Security: Encryption - Design | Security | Encryption | Zara Patel | Sophia Clark | Completed | 100 | 8 | 360 | BIG1036 | Low | Web Portal | 2025-11-27 13:39:00 | 2025-12-05 16:39:00 | Docs required. | refactor,critical
BIG1009 | Payments: Billing - Improve | Payments | Billing | James Scott | Arjun Kumar | Completed | 100 | 12 | 540 | BIG1006 | Critical | Core Platform | 2025-10-19 15:52:00 | 2025-10-25 17:52:00 | QA passed. | refactor,research,security
BIG1010 | Payments: Refunds - Test | Payments | Refunds | Zara Patel | James Scott | Open | 85 | 4 | 100 |  | Medium | Core Platform | 2025-11-18 12:15:00 |  | Blocked by API team. | enhancement
BIG1011 | Security: Vulnerability Fixes - Refactor | Security | Vulnerability Fixes | Mia Lewis | Zara Patel | In Progress | 82 | 12 | 420 |  | Medium | Mobile App | 2025-09-26 13:20:00 |  | Requires design sign-off. | enhancement,performance
BIG1012 | DevOps: CI/CD - Test | DevOps | CI/CD | Lucas Young | Harper Adams | Completed | 100 | 12 | 300 | BIG1037 | Critical | Admin Dashboard | 2025-09-02 13:36:00 | 2025-09-12 14:36:00 | Merge conflict to resolve. | refactor,design,research
BIG1013 | Notifications: Push - Test | Notifications | Push | Rohan Iyer | Noah Davis | Completed | 100 | 24 | 1080 |  | Low | Analytics Suite | 2025-09-24 09:47:00 | 2025-09-30 13:47:00 | Pending security review. | bug,minor
BIG1014 | UI: Dashboard - Implement | UI | Dashboard | Zara Patel | Zara Patel | In Progress | 30 | 16 | 720 | BIG1058 | Critical | Web Portal | 2025-10-02 09:16:00 |  | Requires design sign-off. | research,performance
BIG1015 | UI: Components - Fix | UI | Components | Noah Davis | Mia Lewis | In Progress | 81 | 4 | 180 | BIG1038 | Medium | Mobile App | 2025-11-04 13:44:00 |  | Needs performance tests. | ux,critical,minor
BIG1016 | Security: Encryption - Design | Security | Encryption | Rohan Iyer | Elijah Green | Completed | 100 | 40 | 1800 |  | High | Core Platform | 2025-11-27 10:33:00 | 2025-12-05 18:33:00 | Requires design sign-off. | ux
BIG1017 | API: GraphQL - Fix | API | GraphQL | Noah Davis | Rohan Iyer | In Progress | 62 | 24 | 1080 | BIG1012 | High | Billing System | 2025-11-27 12:45:00 |  | Needs performance tests. | performance,security,refactor
BIG1018 | Payments: Refunds - Improve | Payments | Refunds | Mason Hall | Ethan Walker | In Progress | 5 | 4 | 140 | BIG1055 | High | Admin Dashboard | 2025-09-01 12:37:00 |  | Requires design sign-off. | performance,design
BIG1019 | API: GraphQL - Test | API | GraphQL | Olivia Miller | Olivia Miller | In Progress | 48 | 16 | 720 |  | Medium | Web Portal | 2025-10-19 16:55:00 |  | Blocked by API team. | minor,security,enhancement
BIG1020 | Database: Schema - Improve | Database | Schema | Ella Johnson | Harper Adams | In Progress | 29 | 16 | 720 | BIG1032 | Medium | Web Portal | 2025-11-09 15:34:00 |  | Owner to update status. | minor
BIG1021 | Auth: OAuth - Implement | Auth | OAuth | Mason Hall | Mason Hall | Open | 90 | 40 | 1000 |  | High | Billing System | 2025-09-05 16:38:00 |  | Merge conflict to resolve. | performance
BIG1022 | Security: Encryption - Implement | Security | Encryption | Arjun Kumar | Arjun Kumar | In Progress | 18 | 12 | 300 |  | Medium | Web Portal | 2025-11-16 14:15:00 |  | Requires design sign-off. | enhancement,minor,refactor
BIG1023 | Notifications: SMS - Test | Notifications | SMS | Lucas Young | Ethan Walker | Completed | 100 | 16 | 560 | BIG1024 | Low | Mobile App | 2025-10-11 15:26:00 | 2025-10-14 19:26:00 | Docs required. | performance,security
BIG1024 | Analytics: ETL - Design | Analytics | ETL | Lucas Young | Lucas Young | In Progress | 10 | 40 | 1000 | BIG1058 | Low | API Services | 2025-10-03 12:21:00 |  | Owner to update status. | ux,performance
BIG1025 | Database: Migrations - Refactor | Database | Migrations | Sana Roy | Elijah Green | Completed | 100 | 8 | 360 |  | High | Analytics Suite | 2025-10-13 13:58:00 | 2025-10-14 16:58:00 | Merge conflict to resolve. | research,minor,ux
BIG1026 | Notifications: Email - Refactor | Notifications | Email | Liam Brown | Noah Davis | Blocked | 65 | 12 | 420 | BIG1064 | Low | API Services | 2025-10-16 13:16:00 |  | Merge conflict to resolve. | critical
BIG1027 | Analytics: Events - Design | Analytics | Events | Liam Brown | Amelia Baker | Completed | 100 | 12 | 420 |  | Medium | Billing System | 2025-09-03 13:35:00 | 2025-09-13 19:35:00 | Owner to update status. | refactor,ux
BIG1028 | API: Rate Limiting - Implement | API | Rate Limiting | Olivia Miller | Lucas Young | Completed | 100 | 24 | 600 |  | High | API Services | 2025-11-02 11:58:00 | 2025-11-11 11:58:00 | Requires design sign-off. | research
BIG1029 | API: REST Endpoints - Implement | API | REST Endpoints | Harper Adams | Rohan Iyer | In Progress | 2 | 16 | 720 | BIG1001 | Low | Admin Dashboard | 2025-09-08 16:42:00 |  | Docs required. | security
BIG1030 | Analytics: Events - Improve | Analytics | Events | Noah Davis | Ella Johnson | Blocked | 32 | 24 | 1080 | BIG1046 | High | Core Platform | 2025-10-01 12:39:00 |  | QA passed. | research,ux,design
BIG1031 | UI: Landing - Improve | UI | Landing | Liam Brown | Ethan Walker | In Progress | 1 | 40 | 1000 |  | Low | Analytics Suite | 2025-11-10 16:03:00 |  | Pending security review. | bug,security,performance
BIG1032 | Database: Backups - Fix | Database | Backups | Liam Roberts | Liam Roberts | Review | 72 | 24 | 600 |  | Low | Analytics Suite | 2025-11-27 13:57:00 |  | QA passed. | ux
BIG1033 | Analytics: Events - Fix | Analytics | Events | Sophia Clark | Mia Lewis | Blocked | 42 | 24 | 840 |  | High | API Services | 2025-11-12 15:43:00 |  | Blocked by API team. | bug
BIG1034 | Database: Schema - Fix | Database | Schema | Arjun Kumar | Sana Roy | Completed | 100 | 40 | 1000 | BIG1035 | Medium | Web Portal | 2025-11-16 15:49:00 | 2025-11-22 15:49:00 | Pending security review. | minor,bug,design
BIG1035 | UI: Landing - Fix | UI | Landing | Lucas Young | Lucas Young | In Progress | 40 | 16 | 400 |  | Low | Web Portal | 2025-11-21 11:47:00 |  | Merge conflict to resolve. | bug,enhancement
BIG1036 | API: API Docs - Refactor | API | API Docs | Ava Thompson | Priya Singh | Blocked | 45 | 4 | 100 |  | Medium | Analytics Suite | 2025-10-23 10:01:00 |  | QA passed. | minor,ux
BIG1037 | Security: Vulnerability Fixes - Design | Security | Vulnerability Fixes | Rohan Iyer | Rohan Iyer | Open | 38 | 12 | 420 | BIG1035 | Low | Mobile App | 2025-10-19 11:08:00 |  | Pending security review. | refactor,bug
BIG1038 | Payments: Gateway Integration - Test | Payments | Gateway Integration | Liam Brown | Zara Patel | Blocked | 38 | 8 | 360 | BIG1001 | Medium | Admin Dashboard | 2025-09-26 16:06:00 |  | Pending security review. | critical,minor
BIG1039 | Search: Indexing - Fix | Search | Indexing | Amelia Baker | Liam Brown | Completed | 100 | 16 | 560 | BIG1041 | High | API Services | 2025-11-28 12:30:00 | 2025-12-04 14:30:00 | Merge conflict to resolve. | minor,design
BIG1040 | Notifications: Push - Design | Notifications | Push | Mason Hall | Elijah Green | Blocked | 3 | 24 | 1080 | BIG1094 | High | Mobile App | 2025-11-09 11:43:00 |  | Merge conflict to resolve. | refactor,enhancement
BIG1041 | Payments: Gateway Integration - Fix | Payments | Gateway Integration | Priya Singh | Lucas Young | Completed | 100 | 24 | 1080 | BIG1052 | Medium | Analytics Suite | 2025-10-19 10:28:00 | 2025-10-29 17:28:00 | QA passed. | bug,ux,research
BIG1042 | Notifications: Push - Test | Notifications | Push | Ethan Walker | Sana Roy | Open | 55 | 12 | 300 |  | Low | Mobile App | 2025-11-22 15:48:00 |  | Owner to update status. | ux,security
BIG1043 | Notifications: Push - Refactor | Notifications | Push | Sophia Clark | Ella Johnson | In Progress | 18 | 40 | 1800 | BIG1045 | Medium | Analytics Suite | 2025-09-11 10:53:00 |  | Owner to update status. | bug,refactor
BIG1044 | DevOps: Infrastructure - Improve | DevOps | Infrastructure | Priya Singh | Harper Adams | Open | 82 | 12 | 540 |  | High | API Services | 2025-11-30 10:01:00 |  | Owner to update status. | critical
BIG1045 | Analytics: Dashboards - Implement | Analytics | Dashboards | Ethan Walker | Ethan Walker | Completed | 100 | 16 | 560 | BIG1076 | Medium | API Services | 2025-09-24 15:25:00 | 2025-09-25 18:25:00 | Owner to update status. | bug,ux,enhancement
BIG1046 | Notifications: Push - Refactor | Notifications | Push | Sana Roy | Ella Johnson | In Progress | 76 | 12 | 540 | BIG1050 | Medium | Web Portal | 2025-11-02 17:40:00 |  | QA passed. | design
BIG1047 | Search: Indexing - Test | Search | Indexing | Olivia Miller | Lucas Young | In Progress | 47 | 8 | 360 |  | Medium | Billing System | 2025-10-01 13:07:00 |  | Needs performance tests. | refactor
BIG1048 | Security: AuthZ - Test | Security | AuthZ | Mia Lewis | Mia Lewis | Blocked | 40 | 8 | 360 |  | High | Core Platform | 2025-11-02 13:08:00 |  | Merge conflict to resolve. | security,ux
BIG1049 | DevOps: Infrastructure - Test | DevOps | Infrastructure | Mia Lewis | Zara Patel | In Progress | 72 | 4 | 180 |  | Low | Web Portal | 2025-10-27 16:10:00 |  | Owner to update status. | ux,refactor
BIG1050 | Security: Vulnerability Fixes - Design | Security | Vulnerability Fixes | Ella Johnson | Ella Johnson | In Progress | 92 | 4 | 140 |  | Critical | Core Platform | 2025-11-09 14:34:00 |  | Owner to update status. | refactor
BIG1051 | Notifications: Push - Refactor | Notifications | Push | Liam Roberts | Ella Johnson | Completed | 100 | 40 | 1800 | BIG1079 | Low | Mobile App | 2025-10-01 12:51:00 | 2025-10-11 17:51:00 | Owner to update status. | critical,security,design
BIG1052 | Security: Vulnerability Fixes - Fix | Security | Vulnerability Fixes | Lucas Young | Harper Adams | In Progress | 12 | 40 | 1800 | BIG1018 | High | Web Portal | 2025-10-05 17:57:00 |  | Needs performance tests. | enhancement
BIG1053 | Notifications: Push - Test | Notifications | Push | James Scott | Ethan Walker | In Progress | 48 | 16 | 560 |  | Medium | Analytics Suite | 2025-11-13 13:40:00 |  | Blocked by API team. | critical,refactor,security
BIG1054 | Search: Indexing - Test | Search | Indexing | Mason Hall | Mason Hall | Completed | 100 | 16 | 720 | BIG1028 | High | Billing System | 2025-10-29 14:54:00 | 2025-10-31 22:54:00 | Docs required. | critical,security
BIG1055 | API: API Docs - Fix | API | API Docs | Lucas Young | Liam Roberts | Open | 20 | 4 | 100 | BIG1057 | Low | Billing System | 2025-11-20 16:01:00 |  | Owner to update status. | design,enhancement,ux
BIG1056 | Notifications: Email - Improve | Notifications | Email | Sophia Clark | Sophia Clark | Completed | 100 | 40 | 1800 |  | Medium | Core Platform | 2025-11-23 11:03:00 | 2025-11-30 15:03:00 | Blocked by API team. | bug,enhancement
BIG1057 | Database: Backups - Improve | Database | Backups | Ava Thompson | Ava Thompson | Completed | 100 | 4 | 140 | BIG1030 | Low | Analytics Suite | 2025-09-16 15:44:00 | 2025-09-19 22:44:00 | Blocked by API team. | design,enhancement
BIG1058 | API: GraphQL - Improve | API | GraphQL | Mason Hall | Rohan Iyer | Blocked | 92 | 12 | 300 |  | High | Admin Dashboard | 2025-11-18 11:28:00 |  | Merge conflict to resolve. | enhancement
BIG1059 | Search: Ranking - Refactor | Search | Ranking | Ava Thompson | Sophia Clark | Review | 82 | 12 | 540 |  | Medium | Admin Dashboard | 2025-10-11 11:15:00 |  | Docs required. | design,research,security
BIG1060 | Analytics: Dashboards - Test | Analytics | Dashboards | Lucas Young | Liam Roberts | Completed | 100 | 16 | 560 |  | Medium | Core Platform | 2025-10-01 16:24:00 | 2025-10-03 19:24:00 | QA passed. | ux,minor
BIG1061 | Security: AuthZ - Implement | Security | AuthZ | Rohan Iyer | Zara Patel | Review | 1 | 4 | 100 |  | Low | Core Platform | 2025-09-10 09:37:00 |  | Pending security review. | minor,ux
BIG1062 | Security: AuthZ - Design | Security | AuthZ | Lucas Young | Lucas Young | In Progress | 19 | 8 | 200 | BIG1069 | Medium | API Services | 2025-10-10 10:32:00 |  | Blocked by API team. | research,performance
BIG1063 | UI: Components - Improve | UI | Components | Rohan Iyer | Noah Davis | Completed | 100 | 4 | 100 |  | High | Mobile App | 2025-09-08 13:42:00 | 2025-09-11 14:42:00 | Merge conflict to resolve. | design,enhancement,critical
BIG1064 | Payments: Refunds - Improve | Payments | Refunds | Ava Thompson | Ava Thompson | In Progress | 33 | 4 | 140 |  | Medium | Admin Dashboard | 2025-10-25 13:33:00 |  | QA passed. | enhancement,critical,ux
BIG1065 | UI: Landing - Implement | UI | Landing | Olivia Miller | Rohan Iyer | Open | 46 | 16 | 400 |  | Low | Analytics Suite | 2025-09-02 12:02:00 |  | Requires design sign-off. | critical
BIG1066 | Analytics: ETL - Fix | Analytics | ETL | Harper Adams | James Scott | Completed | 100 | 8 | 280 |  | Critical | Core Platform | 2025-11-13 14:07:00 | 2025-11-22 14:07:00 | Merge conflict to resolve. | bug,security
BIG1067 | Auth: Session - Implement | Auth | Session | Harper Adams | Harper Adams | Blocked | 75 | 12 | 540 |  | High | Admin Dashboard | 2025-10-09 12:29:00 |  | Owner to update status. | performance,research
BIG1068 | Notifications: SMS - Test | Notifications | SMS | Liam Roberts | Ava Thompson | Review | 93 | 40 | 1000 |  | Low | Mobile App | 2025-09-01 15:54:00 |  | Pending security review. | design
BIG1069 | Auth: OAuth - Design | Auth | OAuth | Lucas Young | Olivia Miller | Completed | 100 | 24 | 840 | BIG1018 | Low | Admin Dashboard | 2025-10-18 16:47:00 | 2025-10-20 17:47:00 | Requires design sign-off. | design
BIG1070 | Notifications: Email - Test | Notifications | Email | Olivia Miller | Liam Brown | In Progress | 17 | 8 | 280 |  | Low | Mobile App | 2025-10-05 12:04:00 |  | Merge conflict to resolve. | security
BIG1071 | Database: Backups - Fix | Database | Backups | Noah Davis | Noah Davis | In Progress | 38 | 40 | 1800 |  | Low | Analytics Suite | 2025-09-16 10:10:00 |  | QA passed. | research,critical,minor
BIG1072 | Auth: Session - Fix | Auth | Session | Mia Lewis | Mia Lewis | Open | 70 | 40 | 1000 |  | Medium | Analytics Suite | 2025-10-22 16:35:00 |  | Needs performance tests. | research
BIG1073 | Database: Backups - Fix | Database | Backups | Mason Hall | Mason Hall | Blocked | 25 | 4 | 180 | BIG1083 | High | Core Platform | 2025-10-04 10:01:00 |  | QA passed. | performance,enhancement
BIG1074 | Analytics: ETL - Refactor | Analytics | ETL | Sana Roy | Zara Patel | Open | 27 | 12 | 420 | BIG1024 | Low | Mobile App | 2025-11-27 15:11:00 |  | Requires design sign-off. | design
BIG1075 | Analytics: ETL - Refactor | Analytics | ETL | Sophia Clark | Liam Roberts | Open | 82 | 8 | 280 |  | Medium | Analytics Suite | 2025-10-20 11:26:00 |  | Requires design sign-off. | security,refactor
BIG1076 | Search: Ranking - Fix | Search | Ranking | Amelia Baker | Ethan Walker | In Progress | 3 | 8 | 200 | BIG1100 | Low | Billing System | 2025-09-04 14:38:00 |  | QA passed. | bug
BIG1077 | Database: Indexes - Design | Database | Indexes | Ava Thompson | Liam Roberts | Completed | 100 | 8 | 280 | BIG1076 | High | API Services | 2025-09-29 15:22:00 | 2025-10-02 17:22:00 | QA passed. | critical,enhancement,research
BIG1078 | Security: Encryption - Implement | Security | Encryption | Liam Brown | Zara Patel | Open | 2 | 8 | 200 | BIG1068 | Low | Admin Dashboard | 2025-09-08 12:38:00 |  | Owner to update status. | enhancement,critical,performance
BIG1079 | API: GraphQL - Improve | API | GraphQL | Zara Patel | Rohan Iyer | Completed | 100 | 12 | 300 | BIG1039 | Low | Mobile App | 2025-09-10 14:45:00 | 2025-09-17 15:45:00 | Pending security review. | critical,enhancement,ux
BIG1080 | Search: Indexing - Refactor | Search | Indexing | Ella Johnson | Harper Adams | Completed | 100 | 24 | 1080 |  | Medium | Analytics Suite | 2025-10-08 11:11:00 | 2025-10-09 17:11:00 | Owner to update status. | enhancement,critical
BIG1081 | UI: Dashboard - Fix | UI | Dashboard | Ava Thompson | Liam Brown | Open | 33 | 4 | 140 |  | Medium | Web Portal | 2025-09-12 14:28:00 |  | Docs required. | minor
BIG1082 | Analytics: Events - Refactor | Analytics | Events | Zara Patel | Zara Patel | Completed | 100 | 24 | 600 |  | Low | Core Platform | 2025-10-15 17:24:00 | 2025-10-18 00:24:00 | Requires design sign-off. | design,bug
BIG1083 | Notifications: Push - Refactor | Notifications | Push | Mia Lewis | Mia Lewis | Completed | 100 | 40 | 1000 | BIG1004 | High | Mobile App | 2025-11-10 10:21:00 | 2025-11-20 17:21:00 | Pending security review. | critical
BIG1084 | Database: Backups - Test | Database | Backups | Priya Singh | Priya Singh | Completed | 100 | 8 | 200 |  | Medium | Admin Dashboard | 2025-11-09 13:42:00 | 2025-11-14 17:42:00 | Merge conflict to resolve. | performance,minor
BIG1085 | Payments: Refunds - Test | Payments | Refunds | Zara Patel | Sana Roy | In Progress | 81 | 8 | 360 |  | Medium | Core Platform | 2025-09-13 09:13:00 |  | Docs required. | design,bug
BIG1086 | Security: Encryption - Implement | Security | Encryption | Sophia Clark | Sophia Clark | Completed | 100 | 16 | 720 | BIG1060 | Low | Web Portal | 2025-10-18 11:28:00 | 2025-10-19 15:28:00 | Requires design sign-off. | bug,ux,critical
BIG1087 | Analytics: ETL - Implement | Analytics | ETL | Liam Roberts | Priya Singh | Open | 87 | 24 | 600 |  | Medium | Core Platform | 2025-10-20 17:26:00 |  | Pending security review. | ux,security,enhancement
BIG1088 | DevOps: CI/CD - Implement | DevOps | CI/CD | Mason Hall | Elijah Green | Completed | 100 | 8 | 360 |  | High | Web Portal | 2025-09-17 09:27:00 | 2025-09-19 15:27:00 | QA passed. | minor
BIG1089 | Analytics: ETL - Fix | Analytics | ETL | Arjun Kumar | James Scott | Blocked | 14 | 16 | 720 |  | Low | Admin Dashboard | 2025-09-02 17:50:00 |  | Blocked by API team. | design
BIG1090 | Notifications: Email - Fix | Notifications | Email | Ethan Walker | Ethan Walker | Completed | 100 | 16 | 400 | BIG1019 | Low | Web Portal | 2025-11-13 16:02:00 | 2025-11-16 20:02:00 | Owner to update status. | design,critical
BIG1091 | Notifications: Email - Fix | Notifications | Email | Sana Roy | James Scott | Completed | 100 | 12 | 300 | BIG1096 | High | Web Portal | 2025-11-29 10:55:00 | 2025-12-03 12:55:00 | Docs required. | bug,research,refactor
BIG1092 | Analytics: ETL - Refactor | Analytics | ETL | Rohan Iyer | Rohan Iyer | Completed | 100 | 12 | 300 | BIG1091 | Low | Analytics Suite | 2025-09-08 17:50:00 | 2025-09-11 18:50:00 | Requires design sign-off. | performance
BIG1093 | Auth: Password Reset - Improve | Auth | Password Reset | Noah Davis | Sophia Clark | Completed | 100 | 16 | 720 |  | Medium | Mobile App | 2025-10-06 14:52:00 | 2025-10-14 22:52:00 | QA passed. | refactor
BIG1094 | Security: Encryption - Fix | Security | Encryption | James Scott | Mia Lewis | Completed | 100 | 4 | 180 |  | High | API Services | 2025-10-04 10:18:00 | 2025-10-05 16:18:00 | Owner to update status. | minor,security,performance
BIG1095 | Auth: Password Reset - Implement | Auth | Password Reset | Elijah Green | Mia Lewis | Completed | 100 | 40 | 1800 | BIG1091 | Medium | Billing System | 2025-09-02 12:16:00 | 2025-09-12 16:16:00 | QA passed. | design,security
BIG1096 | Analytics: ETL - Improve | Analytics | ETL | Ava Thompson | Ava Thompson | Blocked | 76 | 40 | 1400 | BIG1078 | Low | Core Platform | 2025-11-24 14:35:00 |  | Merge conflict to resolve. | critical,design
BIG1097 | Payments: Gateway Integration - Implement | Payments | Gateway Integration | Liam Roberts | Rohan Iyer | Completed | 100 | 40 | 1800 | BIG1004 | Critical | Web Portal | 2025-09-08 15:42:00 | 2025-09-14 17:42:00 | Pending security review. | ux,research,critical
BIG1098 | Database: Backups - Test | Database | Backups | Liam Brown | Sophia Clark | Blocked | 12 | 12 | 300 |  | High | API Services | 2025-09-22 17:11:00 |  | Needs performance tests. | bug,research,critical
BIG1099 | Payments: Billing - Fix | Payments | Billing | Ethan Walker | Sophia Clark | In Progress | 60 | 4 | 100 |  | Medium | Mobile App | 2025-10-08 16:54:00 |  | Blocked by API team. | design,minor,performance
BIG1100 | API: GraphQL - Fix | API | GraphQL | Olivia Miller | Olivia Miller | Review | 23 | 40 | 1400 |  | Medium | API Services | 2025-10-29 11:20:00 |  | Needs performance tests. | performance

## Component_Summary
Component | Task Count
Analytics | 16
Notifications | 16
Security | 13
Payments | 11
Database | 10
API | 9
Auth | 7
UI | 7
Search | 6
DevOps | 5